IMC PM TOOLKIT · SESSION 2 · WORKED EXAMPLE · NUTRICOL

Project Canvas

One page, four domains (Why · Who · What/How/When · Where). A fuller brief for bigger or cross-functional projects — based on Antonio Nieto-Rodriguez's Project Canvas.

| Why — rationale & purpose Purpose: Deliver a market-ready OEM marine-collagen sachet product for the K-Beauty client, from signed brief to first mass-production batch, by 30 Sep 2026. Business rationale: Opens an OEM revenue line with a K-Beauty client and proves IMC can run marine-collagen sachet production end-to-end. | Who — accountability & governance Sponsor: Deputy GM, Operations — approves scope, charter changes and the budget. Owner (Accountable): PM — NutriCol. One name; answers for the project. Resources / team: Function Leads: BD · R&D · QA · Production. Governed by the RACI on the governance one-pager. |
| --- | --- |
| What · How · When — definition, plan & risk Deliverables (in scope): Sachet formulation & R&D · stability/dissolution testing · QA release criteria · packaging & artwork · pilot + first mass-production batch · export regulatory dossier. Out of scope: Customer marketing/branding/pricing · distribution after FOB · a 2nd variant · after-sales / consumer support. Plan & milestones: 4 work streams (R&D · QA/regulatory · packaging · production). Pilot batch then first mass-production batch by 30 Sep 2026. Re-baseline +2 wks once CR is approved. Top risks (from RAID): C-01 spec change in change control · D-01 peach-flavor material 4-wk lead time (the constraint) · R-01 higher dose may fail stability. Stakeholders: K-Beauty customer · Sponsor & leadership portfolio review · regulatory affairs. Change approach: ONE spec change (flavor + dosage) absorbed in the current timeline; any further change goes through change control and may move the date. |  |
| Where — organization & context Context: OEM build for an external K-Beauty client; cross-functional inside IMC; the project's weekly RAG report rolls up to the portfolio review above it. |  |

Heartbeat — the weekly rhythm

Weekly project sync — Thursdays 09:00 (PM + Function Leads); the 1-page RAG report is produced at that sync and feeds the portfolio dashboard.

The Project Canvas is an alternative to the 1-page charter — a fuller brief for bigger or cross-functional work. Same Goal / Scope / Owner feed the RAG report. · IMC PM Training, Session 2.