IMC PM TOOLKIT · SESSION 2 · WORKED EXAMPLE · NUTRICOL

Project Charter

The 1-page contract. Frame the project before it starts; review it at the first meeting.

Project

NutriCol — Marine Collagen OEM Launch

| Sponsor | Deputy GM, Operations |
| --- | --- |
| Project manager (owner) | PM — NutriCol |
| Date written | 25 May 2026 |
| Target close | 30 Sep 2026 — first mass-production batch |

1 · Goal — one sentence

Deliver a market-ready OEM marine-collagen sachet product for the K-Beauty client, from signed brief to first mass-production batch, by 30 Sep 2026.

2 · Scope

| IN — we will deliver | OUT — we will not |
| --- | --- |
| • Formulation & R&D of the marine-collagen sachet • Stability and dissolution testing • QA sign-off and release criteria • Packaging & artwork coordination with the customer • Pilot batch + first mass-production batch • Export regulatory dossier | • Customer's own marketing, branding and retail pricing • Distribution & logistics after FOB • A second product variant (deferred to a later project) • After-sales / consumer support |

Contested boundary — read this out loud at kickoff

ONE spec change (flavor + dosage) is absorbed within the current timeline. Any further change goes through change control and may move the date.

3 · Owner (Accountable)

PM — NutriCol. One name. The person who answers for the project.

4 · Plan — work streams

| Work stream | Lead |
| --- | --- |
| Formulation & R&D | R&D Lead |
| QA, stability & regulatory | QA Lead |
| Packaging & artwork | BD Lead |
| Production readiness & pilot batch | Production Lead |

5 · Heartbeat — the weekly rhythm

Weekly project sync — Thursdays 09:00, 60 min (PM + Function Leads); the 1-page RAG report is produced at that sync. Each function runs its own ~30-min team weekly.

Charter feeds the SCOPE dimension of the RAG report. No charter → Scope is Red by default. · IMC PM Training, Session 2.