IMC PM TOOLKIT · SESSION 2 · WORKED EXAMPLE · NUTRICOL

Governance — one page

Who decides (RACI) · how we meet (cadence) · how we escalate. The project's operating system.

1 · RACI — who decides what

R = Responsible (does it) · A = Accountable (answers for it — exactly ONE per row) · C = Consulted · I = Informed

| Decision / deliverable | Sponsor | PM | BD Lead | R&D Lead | QA Lead | Production Lead |
| --- | --- | --- | --- | --- | --- | --- |
| Approve project charter & scope | A | R | C | C | C | C |
| Approve a spec / requirement change (CR) | A | R | C | C | C | C |
| Final formulation sign-off | I | I | C | A | C | I |
| QA / stability test plan & product release | I | I | C | C | A | I |
| Customer communication & commercial terms | I | C | A | I | I | I |
| Pilot batch & production readiness | I | I | I | C | C | A |
| Weekly status report to leadership | I | A | C | C | C | C |

2 · Cadence — one rhythm, three lenses (all weekly)

| Meeting | Length | Who | Focus |
| --- | --- | --- | --- |
| Team weekly | ~30 min | Each Function Lead | Activities & blockers in that function |
| Project weekly | ~60 min (Thu 09:00) | PM + Function Leads | Cross-functional decisions, RAID review, status |
| Portfolio weekly | ~60 min | Sponsor + PMs | Priorities & resource conflicts across projects |

3 · Escalation path

Step 1 — Project level — Blocker raised at the Project weekly. PM resolves with the Function Leads within 48 hours.

Step 2 — Sponsor — If unresolved, or it needs authority / budget / a scope change beyond the charter allowance, escalate to the Sponsor. Decision within 3 working days.

Escalate immediately when: a scope change exceeds the charter allowance · the date slips more than 1 week · two functions are deadlocked.

The 'A' column makes hidden ownership conflicts visible — it feeds decision speed & the Resources dimension of the RAG report. Cadence feeds Schedule visibility. · IMC PM Training, Session 2.