## RAID
ID | Type | Description | Likelihood | Impact | Owner | Next action | Due | Status
C-01 | Change | Customer changed flavor (lemon→peach) and dose (2,500→5,000 mg) after R&D started. |  | H | PM | Log CR; re-baseline timeline (+2 wks); get Sponsor approval. | 03 Jun | In progress
D-01 | Dependency | [CONSTRAINT] Peach-flavor raw material has a 4-week supplier lead time — gates the pilot batch. |  | H | BD Lead | Place PO this week; confirm delivery date. | 30 May | Open
I-01 | Issue | QA and Production were engaged late; no pilot-line capacity is booked. |  | H | Production Lead | Book pilot-line slot for week of 22 Jun. | 02 Jun | Open
R-01 | Risk | Higher 5,000 mg dose may fail dissolution / stability at room temperature. | M | H | R&D Lead | Run accelerated stability test on the new dose. | 15 Jun | Open
R-02 | Risk | Export regulatory dossier may need re-filing for the new dose. | M | M | QA Lead | Confirm re-filing requirement with regulatory affairs. | 10 Jun | Open
I-02 | Issue | Packaging artwork still shows the old flavor and dose. |  | M | BD Lead | Brief design to update artwork after CR sign-off. | 12 Jun | Open
A-01 | Action | Re-baseline the project schedule once the CR is approved. |  | M | PM | Issue revised plan + new heartbeat dates. | 05 Jun | In progress
A-02 | Action | Get the customer's written sign-off on the revised spec. |  | H | BD Lead | Send revised spec sheet; obtain email confirmation. | 03 Jun | Open
Type: Risk (might happen) · Action (to do) · Issue (already happening) · Dependency (waiting on) · Change (scope/requirement change). Likelihood/Impact = H/M/L (risks). Flag your CONSTRAINT in Dependencies.