IMC PM TOOLKIT · SESSION 2 · WORKED EXAMPLE · NUTRICOL

RAG Status Report

The weekly 1-page snapshot. Color is a conversation starter, not a verdict.

| Project | Report date | PM | Sponsor |
| --- | --- | --- | --- |
| NutriCol — Marine Collagen OEM Launch | 29 May 2026 | PM — NutriCol | Deputy GM, Operations |

Outcome (one sentence)

Deliver a market-ready OEM marine-collagen sachet product for the K-Beauty client, from signed brief to first mass-production batch, by 30 Sep 2026.

Status by dimension

| Dimension | R/A/G | Why (if not green) | Next action — owner |
| --- | --- | --- | --- |
| Scope | Amber | One spec change is in change control (CR not yet approved). | PM |
| Schedule | Red | Re-baseline +2 weeks; pilot line not yet booked. | Production Lead |
| Cost | Green | — | — |
| Risk | Amber | Stability of the higher dose is under test. | R&D Lead |
| Resources | Amber | QA & Production engaged late; capacity being secured. | Production Lead |

Overall: Amber

Top items this week (pulled from the RAID log)

C-01 — Spec change in change control (Sponsor approval pending).

D-01 — Peach-flavor material 4-week lead time (the constraint).

I-01 — Pilot-line capacity not yet booked.

Each Amber/Red gets ONE line of why + a named owner. Color tells the room what to talk about. This report is the unit that feeds the Session-1 portfolio dashboard. · IMC PM Training, Session 2.